## Instructions
Tab | Description/Purpose
Rating Reference | Brief Description to describe the different ratings for each area: People, Process and Technology. Ratings will help populate statistics (i.e. rating = degree and level of impact).
Impact Analysis | Captures verbatim comments and ratings gathered from stakeholders during impact assessment workshop(s). Each comment is entered against each sub-category including the rating. The project impact rating then provides a weighted rating for each sub-category.
Summary | Provides an average for each sub-category which is then rolled up to provide an overall impact rating for all nine categories. This information is then used to populate the spider graph.
Spider Graph | A graphical illustration of the nine impact category ratings.

## Rating reference
Impact Type | Description | Impact (depth and breadth) of change required |  |  | Change activities (examples)
|  | High | Medium | Low
People (internal) | Impacts may include changes to roles, responsibilities, skills, knowledge, organisation structure and/or location. Include consideration of whether different work groups or roles are affected differently or the same | Number of impacted staff is more than one Branch AND/OR across multiple geographic locations AND/OR more than 500 staff. Skills require deep expertise in a wide range of areas OR major change to roles and responsibilities. | More than 100 impacted staff AND/OR more than one workgroup within the same Branch . Requires deep expertise in a few new areas, roles or readily learned skills in wider areas OR minor change to roles and responsibilities. | Number of impacted staff is a workgroup or less than 50. New knowledge and skills can be implemented within the existing skill sets. | Leadership activities, engagement, communication, Workshops, documentation, training (if ‘complex’)
Processes | Business processes, including decision making. How many process flows are changed, how many staff (users) are affected across how many geographic locations. What is the volume (high/medium/low) of transactions using these processes. How many processes are changed (high/medium/low). | Major change to wide set of processes AND/OR major negatives for many stakeholders | Moderate changes to wide set of processes OR major changes in a narrow group OR major negative for a few stakeholders | None/minimal process changes required and positives and negatives about equal for stakeholders | Process mapping, leadership, workshops, documentation, training, system support
Technology | Changes to the functionality, usability, availability and reliability of technology systems. How many systems are likely to be affected? How much of a difference between current state and future state? To what extent does the success of the change rely on technology changing? Will access to technology change | Replacement of the majority or all existing systems; may include software applications, networks, infrastructure. | Substantial changes to the functionality of existing information systems OR implementation of currently unused functionality OR implementation of a new system. | Some changes to the functionality of the existing systems. Some changes to users roles and responsibilities. Minimal changes to the ICT infrastructure/user interfaces/ reports. | Development and roll out of new functionality, skills gap analysis, training and documentation.
People (external) | The impacts on current or potential new contracted providers of services or other externals, e.g. other agencies The impacts on current or potential new customers or customer groups, e.g. visa applicants, Chinese applicants, employers | Major changes to externals, providers or scope of contracts. Major changes to customers or customer groups. | Moderate changes to externals, providers or scope of contracts. Moderate changes to customers or customer groups. | No or minimal change to externals, providers or scope of contracts. No or minimal change to customers or customer groups. | Interagency collaboration/workshops Leaders/Vendor engagement New contract forms New contract management approaches, documentation & training.
Other | E.g. Privacy and data collection Reporting Finance- new, altered or stopped revenue? Contractual - e.g. contracts with external providers, VACs, vendors? MoUs? | Major changes OR major negatives for many users | Moderate changes OR major negatives for a few users | No/minimal changes required & balance of positives/ negatives for users | Anything not covered elsewhere
Publications and Products | Changes may impact template letters, forms, guides, website content, and/or user manuals. | Major changes to some publications and products AND / OR minor changes to a large number of publications and products. | Some changes to some publications and products OR major changes to a small number of publications and products. | Minor changes to some publications and products. | Updates to published content, either external, online or internal
Policy & Legislation | Policy (big ‘P’ and little ‘p’ policy) legislative, regulatory and internal changes. For example, financial delegations, health and safety, security, privacy, enterprise architecture, information management | Major change to wide set of policies AND/OR major negatives for many stakeholders | Moderate changes to wide set of policies OR major changes in a narrow group OR major negative for a few stakeholders | None/minimal policy changes required and positives and negatives about equal for stakeholders | Policy review, leadership, workshops, documentation, training, communication
Culture & behaviour | The change means that attitudes, core values or beliefs are impacted. Current behaviours and attitudes may need to stop | Major change in behaviour or attitude is required across a range of groups / areas. | Requires significant behaviour or attitude changes amongst a few small groups OR a few minor changes across a number of groups. | The change can be implemented without major changes to any behaviours and attitudes. | Leadership, workshops, learning, various means of reinforcement e.g. rewards
Property, Equipment and Facilities | Changes to the location, type and availability of property, facilities and equipment. Includes whether access to buildings needs changing, new hardware is required and/or new equipment needs to be provided or old equipment removed. | Extensive replacement of the majority or all existing facilities and equipment. More than one team is moving location as a result of the change. | Substantial changes to the existing facilities and equipment. A team is moving location as a result of the change. | Some changes to equipment and facilities. | New buildings, hardware, availability of services etc.

## Impact Analysis
BCI Change Impact Assessment |  |  |  | People (Internal) | [15 empty] | Process | [7 empty] | Technology | [11 empty] | People (External) | [13 empty] | Other | [9 empty] | Publications & Products | [7 empty] | Policy & Legislation | [7 empty] | Culture & Behaviour | [5 empty] | Property, Facilities & Equipment
|  |  |  | Roles & Tasks |  | Accountabilities & Responsibilities |  | Organisation Structure & Team Composition |  | Key Performance Measures |  | Capabilities and Skills | Impact | Resourcing | Impact | Impact to Teams | Impact | Workload | Impact | Business Processes |  | Delivery of Service | Impact | Dependencies |  | Interaction |  | Applications |  | Desktop Environment |  | Data | Infrastructure | Infrastructure | Infrastructure | Vendor Management | Service Management Capability | Service Management Capability | Service Management Capability | Ministers & Advisors |  | Government |  | Customers |  | VACs |  | Agencies |  | Employers |  | Specialist Groups |  | Finance |  | Privacy |  | Reporting |  | Contractual |  | Health and Safety |  | Process Inputs |  | Process Outputs |  | Templates |  | Products |  | Policy |  | Legislation |  | Delegations |  | Policy or business rules |  | Culture |  | Behaviour |  | Core Values |  | Property |  | Equipment |  | Facilities
|  |  |  | • Will this require any changes to roles or the scope of tasks undertaken? |  | • Any changes to the accountabilities and responsibilities for roles? |  | • Will there be any changes to teams or to where roles are located in the overarching business units or business groups? |  | Will there be any changes to any key performance measures for teams or individuals? |  | • Any changes to the capabilities or skills that our people require to carry out their roles? |  | • What capabilities and how many people will be required to design and implement this change? |  | • How many of our people does this change impact? L = 1-100 M=100-500 H = 500-1000 |  | • How much work will this create? • Any changes in the activities/amount of work that teams are required to carry out? |  | • Any changes to the processes or services that the business delivers? |  | • Any changes to the way in which teams deliver services (to internal or external customers) |  | • Will there be any changes to process/team interdependencies in order to deliver a process or service? |  | Will the team need to interact with new (or no longer) internal or external stakeholders? |  | • Any changes to applications needed to deliver a service? |  | • Any changes to the desktop environment for staff? Desktop- microsoft office excel |  | • Any changes to the way in which data is managed/stored within the organisation? |  | • Any changes to technology infrastructure (e.g. Servers, networks, middleware)? |  |  |  | • Any changes to the capabilities or processes required for IT support and operations management? |  |  |  | • Key agencies • Other agencies |  | • Applicants - What change will customers experience? |  | • Visa Application Centre Offices |  | • Will immigration advisors be impacted? |  | • Businesses |  | • Reference groups • Media • Unions • Other groups to be identified or established e.g. stakeholder panels |  | • Any changes to operational budgets or delegations |  | • Will there be considerations to individual privacy |  | • Are new reports required or changes to existing reporting? |  | • Are there any impacts to contractual agreements with vendors or other staff? |  | • Does this have any impact on the physical and psychological wellbeing of staff/contractors/visitors? |  | • Any changes to the information that teams require to deliver a service, either in terms of its content or source? |  | • Any changes to the products or output for a service? |  | • Any changes to templates both internal and external? |  | • E.g. website information, forms and guides, settlement information, MOU |  | • Any changes to policies needed to support a new service or way of working. For example: -Sections of the business Operating Manual |  | • Any changes to legislation required? For example: Immigration Act 2009, Immigration Regulations, Other |  | • Are there any delegation changes for staff to complete the task? Are there any financial delegation changes |  | • Any changes to Policies or Business Rules needed to support a new service or way of working? |  | • Will there be any impacts to the branch/team OR organisations attitudes or beliefs |  | • Will there be any impact to staff behaviour as a result of the change? |  | • Will there be any impacts to any core values for the business/team? |  | • What changes are needed to ensure property needs are enabled? |  | • What changes are needed to ensure equipment needs are enabled? |  | • What changes are needed to ensure facility needs are enabled?
|  |  |  | • How is the change likely to affect job design? • What positions are impacted? • What is the likely impact on current jobs? • Is there a completely new job to consider? • How does the job fit with organisational outcomes? • Will the job meet MBIE's job design principles? • Is the new job built around complete pieces of work and clear objectives? |  | • How is the change likely to impact the accountabilities and/or responsibilities and expected outcomes for a position? • Can current staff perform the position? |  | • Any change to where the work will be carried out? • Are there adjustments required to employment agreement conditions? • Do the employment agreements require consultation with staff/unions? • Will the nature of the change require an implementation process to be developed with unions? • At what point do unions need to be notified of the project? • Will some staff be released? • Will contractors be required and for how long? |  | • What will be the impact on current operational plans, job expectations job sizing and performance objectives? • Are there additional motivational or incentive requirements? • Does the title reflect the complexity of job content? • Will existing work tracking systems still perform appropriately? |  | • List any changes to competency and behaviour requirements. • How do any new requirements affect current staff e.g., training and development requirements and costs? • Are there any quality implications? • How is the change likely to impact the required leadership/management behaviours? • Are they currently present in the organisation? How many FTE days of training will be needed? |  | • Will staff be sourced internally or will contractors be required? For how long? • What skills are required for design and implementation? • What capcity is needed to maintain BAU and mange the change after implementation? |  |  |  | • How will this impact exisiting work loads on teams? • What pressure will be placed on teams? |  | Any changes to the processes or services that the business delivers? What will be the likely volume of transactions that use these business processes (H, M or L)? Will the likely difference between current state and future state business process change have an H, M or L impact? What internal business process changes are likely and on what scale (H, M or L)? How many business processes are likely to be impacted and on what scale (H, M or L)? Will there be any transitional/interim processes? Will the Visa Assessment Tool be impacted? |  | • How will procedures be impacted? • What engagement services will be impacted by the change? • How will the change impact Service Level Agreements? • How will the change impact supporting documentation requirements? |  | • What areas or groups will need to be consulted to ensure dependencies are captured? |  | • What processes will need to be established, reviewed, developed to enable interaction? • What tools are required? |  | Any changes to applications needed to deliver a service? Applications- servers network What technology impacts are coming? To which system? A new system? A new tab or screen? A new field on a screen? New functionality? Will data need to be migrated from one system to another? |  | Any changes to the way in which data is managed/stored within the organisation? What will the likely impact be on the Data Warehouse? |  | Any changes to the way in which data is managed/stored within the organisation? What will the likely impact be on the Data Warehouse? Is there new data requirements that will need to be monitored and reported on? |  | Any changes to technology infrastructure (e.g. Servers, networks, middleware)? Servers- runs shared company systems networks- drives emails printers middleware-in-house |  | Does the change involve vendors and if so, who? What is the likely scale of their involvement |  |  |  | • Is there messaging Ministers and Advisors will need to receive? • Are there changes to systems to enable the support for this group? Are there impacts to these specific groups Minister of Immigration Associate Minister of Immigration Other (Op Pol can advise if any other specific Ministers should be noted) |  |  |  | Will there be a change of process for these customers? Will customers see a new look and feel? Is there an impact to the current behaviour and culture? |  | How will VAC’s be impacted by the change? Does this include all VAC sites? |  |  |  | Will there be any change of action for employers? How will employers be impacted? What are some considerations that need to be included in the design to ensure employers adopt the change? |  |  |  | Will there be any financial impact – new revenue, altered revenue, stopped revenue? Any changes to operational budgets or delegations? |  |  |  | Will any reports be impacted? What might the business want to report on once the change is live? How will we measure successful implementation in the medium and long term? Will aspects of this work be audited in the future? How will we know that the change is giving us quality data or quality decisions? Is the Data Warehouse impacted? |  | Will any contracts with external providers, VACs, Vendors etc. be impacted? What about Memoranda of Understanding? | [9 empty] | Which Standard Operating Procedures (SOPs) are impacted
Branch | Team | Role | Change Impact (Avg.) | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Impact Description | Rating | Count | Calc
[92 empty] | 0 | 0
[92 empty] | 0 | 0
[92 empty] | 0 | 0
[92 empty] | 0 | 0
[92 empty] | 0 | 0
[92 empty] | 0 | 0
[92 empty] | 0 | 0
[92 empty] | 0 | 0
[92 empty] | 0 | 0
CRIS | [91 empty] | 0 | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0

## Summary
Area Overall |  | Area Impact | [8 empty] | Area Score | [8 empty] | People (Internal) | [7 empty] | Process |  |  |  | Technology | [5 empty] | People (External) | [6 empty] | Other |  |  |  |  | Publications & Products |  |  |  | Policy & Legislation |  |  |  | Culture & Behaviour |  |  | Property, Facilities & Equipment
Overall Rating | Average Score | People (Internal) | Process | Technology | People (External) | Other | Publications & Products | Policy & Legislation | Culture & Behaviour | Property, Facilities & Equipment | People (Internal) | Process | Technology | People (External) | Other | Publications & Products | Policy & Legislation | Culture & Behaviour | Property, Facilities and Equipment | Roles & tasks | Accountabilities & Responsibilities | Organisation Structure & Team Composition | Key performance measures | Capabilities and skills | Resourcing | Impact to teams | Workload | Business Processes | Delivery of Service | Dependencies | Applications | Applications | Desktop environment | Data | Infrastructure | Vendor Management | Service management capability | Ministers & Advisors | Government | Customers | VACs | Agencies | Employers | Specialist Groups | Finance | Privacy | Reporting | Contractual | Health and Safety | Process Inputs | Process Outputs | Templates | Products | Policy | Legislation | Delegations | Policy or business rules | Culture | Behaviour | Core Values | Property | Facilities | Equipment

## Lookup Table
BSG | Visa Services | SPA | CRIS | SDP | Market Services | Other
Business Strategy & Governance | Business & Specialist | Relationship Management | Border Officers (Onshore) | BCI | ICC | Other
Other | Education & Tourism | Settlement | Border Officers (Offshore) | ICT Systems | Other
| Risk & Verification | Skills & Investment | Business Analysts | Immigration Health Team
| Performance & Support | Refugee & Protection | Compliance | Operational Policy
| Transition | Marketing | Identity | Quality & Assurance
| VS2020 | Other | Intelligence | Project Management Office
| Other |  | Risk | Resolutions
|  |  | Other | Insights & Design